## Sprints_Backlog_Book_Management
Task Name | Estimate Time (hour) | Taken by | Actual Time | Status | Date Doing | Note
Requirement of admin analyst | 6 | Do Minh Duc | 3 | Done | 2020-03-18
Draw Class diagram | 3 | Do Minh Duc | 1 | Done | 2020-04-03
Draw Sequence diagram | 6 | Do Minh Duc | 4 | Done | 2020-04-03
[GUI] Admin Form | 3 | Do Minh Duc | 2 | Done | 2020-03-19
[GUI] Login Form | 2 | Do Minh Duc | 1 | Done | 2020-03-19
Check Login | 2 | Do Minh Duc | 1 | Done | 2020-03-19
Add Book | 2 | Do Minh Duc | 1 | Done | 2020-03-20
Update Book | 2 | Do Minh Duc | 1 | Done | 2020-03-20
Delete Book | 2 | Do Minh Duc | 1 | Done | 2020-01-20
Search Book | 2 | Do Minh Duc | 1 | Done | 2020-01-20
Get Book | 2 | Do Minh Duc | 1 | Done | 2020-01-20
Log out (Admin form) | 1 | Do Minh Duc | 1 | Done | 2020-01-20
User Guide: Admin | 1 | Do Minh Duc | 1 | Done | 2020-04-03
Draw System Architecture Diagram | 1 | Do Minh Duc | 1 | Done | 2020-04-03
Total | 35 |  | 57.14%
Requirement of user analyst | 4 | Le Phuong Vinh | 3 | Done | 2020-03-18
[GUI] User Form | 1 | Le Phuong Vinh | 1 | Done | 2020-03-23
Borrow Book | 2 | Le Phuong Vinh | 2 | Done | 2020-03-24
Return Book | 2 | Le Phuong Vinh | 2 | Done | 2020-03-25
Search book by like name | 1 | Le Phuong Vinh | 0.5 | Done | 2020-03-26
Search book by author | 1 | Le Phuong Vinh | 0.5 | Done | 2020-03-27
Draw ER diagram | 2 | Le Phuong Vinh | 1 | Done | 2020-03-21
Draw UseCase diagram | 3 | Le Phuong Vinh | 3 | Done | 2020-03-22
User Guide: User | 2 | Le Phuong Vinh | 2 | Done | 2020-03-29
Collect data and complete document | 2 | Le Phuong Vinh | 2 | Done | 2020-04-05
Create Database | 2 | Le Phuong Vinh | 2 | Done | 2020-03-19
Log out (User form) | 1 | Le Phuong Vinh | 0.5 | Done | 2020-03-23
Load data to user form | 1 | Le Phuong Vinh | 1 | Done | 2020-03-23
Table relationship diagram | 1 | Le Phuong Vinh | 1 | Done | 2020-03-21
Total | 25 |  | 76%